| Goals: Improve the effectiveness of the delivery of health services through SBHCs for children who qualify for medical assistance Improve the coordination of the care of patients services by CCOs and SBHCs |
| --- |
| Objectives 1: Develop viable APMs that allow SBHCs to operate within the ideal SBHC delivery care model and supports SBHC sustainability |
| Activities | Action Steps | Outcome | Timeframe |
| Conduct analysis of current APM landscape in Oregon and nationally | Identify APMs taking place in Oregon Identify APMs taking place nationally | List of APMs that SBHCs could modify to fit their specific needs with regards to service delivery and care coordination | October - November 2014 |
| Define the ideal SBHC program | List of ideal services List of which provider could do each service Frame services using the OHA engagement touches report | Prioritized list of current non-reimbursable SBHC services | November -December2015 |
| Define unique value of SBHCs | Define in payor language Define within Healthcare Transformation How do APMs better support SBHCs | Agreed upon definition of the value that SBHCs bring to the healthcare field | December 2014 |
| Develop service delivery model specific for APMs | Define outcomes Identify processes, workflows, needs | A service delivery model that is supported by both SBHCs and CCOs that improves patient care | January- February 2015 |
| Hire Financial Consultant | Research different health care consultants that have worked on APMs Contact consultants | Financial consultant hired | January 2015 |
| Develop payment models to support ideal SBHC service delivery model | Align revenue to match services Align incentives to match each model | Selection of APMs that are SBHC specific and feasible | February – March 2015 |
| Run financial forecasting on developed APMs | Identify SBHC data set to run forecasting with Identify any changes in service delivery based on specific models | List of APMs that ensures the best coordination and flexibility for SBHCs to provide services | April – May 2015 |
| Objective 2: CCOs and TriCounty SBHCs collaboratively commit to APMs for implementation |
| Activities | Action Steps | Outcome(s) | Timeframe |
| CCO and SBHC leadership meet to review proposed APM options | Review list of SBHC APMs developed by APIP workgroup | Identify APM to pilot during FY 16 | June 2015 |
| Identify participants to pilot SBHC APM | Identify SBHC site that is financially stable and has capacity Identify CCO partner | Contract/MOU process is initiated to implement SBHC APM pilot | June 2015 |
| Objective #3: Develop process for SBHC and CCO collaboration with regards to alternative payment models |
| Activities | Action Steps | Outcome(s) | Timeframe |
| Conduct analysis of current SBHCs having success with coordinating with private providers | -Identify States, SBHCs programs, etc | - List of “key take a ways” and lessons learned from examples found | January 2015 |
| Document process for convening SBHC APIP workgroup | Record all APIP activities done over project period Identify “best practices” | Report outlining analysis and planning process of APIP workgroup | May 2015 |